## January
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
January daily check list
Clear the snow from the road and gate.
Clear snow from disposal area as best as is practical to minimize the generation of leachate when the snow melts.
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log all hours worked.
Notes:
January weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and ensure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
January monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Work with administration on budget for the following year. Plan all the O&M maintenance activity's for the summer.
Plan public education outreach, school presentation, and council meeting.
Assess any heavy equipment needs.
Ensure landfill permit is up to date - renew landfill permit if needed.
If applicable, ensure access to the correct location for public disposal.
Plan to obtain Continuing Education Units (CEUs) for any licenses/certifications. Submit application to the State for RALO. (if applicable under RALO)
Refresh Basic Life Support (BLS) or heart saver first aid and Cardiopulmonary Resuscitation (CPR) if applicable.
If possible, consolidate and compact cell.
Order personal protective equipment, gloves, earplugs, eye protection.
Look for funding and training opportunities. If applicable complete the IGAP funding application.
Order supplies, fence repair equipment, equipment parts, signage.
Notes
Signature Landfill Operator: | Date

## February
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
February daily check list
Clear snow from the road and gate.
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage are.
Secure equipment and gate.
Log the hours worked.
Notes:
February weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
February monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Work with administration on budget for the following year. Plan all the O&M maintenance activity's for the summer. And contact vendors for green-up/clean-up donations.
Plan public education outreach, school presentation, and council meeting.
If possible, consolidate and compact cell.
If applicable, submit applications for beach clean-up and backhaul grants.
Order ALPAR Bags from ConocoPhillips Alaska, Inc. before April 1st.
Notes
Signature Landfill Operator: | Date

## March
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
March daily check list
Clear snow from the road and gate.
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log the hours worked.
Notes:
March weekly check list
If applicable, collect elder/customer waste for disposal.
Control snow to allow for free flowing ditches and dry access roads.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
March monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
If applicable, order hydrated lime for bio-waste cell.
Order grass seed (for closed cells). Schedule community green-up/clean up.
Submit applications for state HAZWOPER.
Order ALPAR Bags from ConocoPhillips Alaska, Inc. before April 1st.
If possible, consolidate and compact cell.
Notes
Signature Landfill Operator: | Date

## April
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
April daily check list
Clear snow from the road and gate.
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log hours worked
Notes:
April weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
April monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Clear ditches and monitor runoff to ensure there is not any standing water during spring thaw.
Change oil and lube in any heavy equipment.
Contact shipping vendors for backhauling.
If ALPAR bags were ordered before April 1st, schedule May community clean up.
Clear grass and brush from burn box area. (50 foot radius)
Schedule May household hazardous waste collection event.
Contact shipping vendors for backhauling.
Consolidate, compact and cover working cell.
Notes
Signature Landfill Operator: | Date

## May
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
May daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log the hours worked.
Notes:
May weekly check list
If applicable, collect elder/customer waste for disposal.
Check for signs of settlement, water pounding, leakage, thermal instability, frost action, or erosion.
Check for signs of leachate outside the landfill.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
May monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
If applicable, open bio-waste cell (septage pit).
Open summer cell - dig a summer cell no more then 4 feet deep with a gradual slope. There must be at least 10 feet of separation between the bottom of the trench and ground water.
Close winter cell - cover and compact closed cells.
Stockpile cover material. If practical, utilize material from digging the summer cell.
Advertise community household hazardous waste collection and prepare shipment for back haul.
Clear grass and brush from burn box area. (50 foot radius)
Conduct household hazardous waste collection and consolidation.
Change oil and lube in any heavy equipment.
Update signage if hours have changed for summer.
Notes
Signature Landfill Operator: | Date

## June
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
June daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log the hours worked.
Notes:
June weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
June monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Close winter cell - compact and apply at least 4 inches of cover to close the winter cell.
Complete community hazardous waste collection. Package and prepare for backhaul two weeks before barge.
Organize salvage yard and waste oil collection.
Maintain road access (brush clearing - fill potholes).
Clear grass and brush from burn box area (50 foot radius).
Repair fence and gate.
Assess personal protective equipment (PPE) and order new PPE if needed.
Train backup operator(s). And plan subistence season schedules.
Consolidate, compact and cover working cell.
Notes
Signature Landfill Operator: | Date

## July
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
July daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log the hours worked.
Notes:
July weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
July monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Stockpile cover material.
Repair fence and gate.
Inspect drainage.
Repair any drainage issues.
Clear grass and brush from burn box area (50 foot radius).
Complete Freon removal.
Consolidate, compact and cover working cell.
Notes
Signature Landfill Operator: | Date

## August
SWO Annual Plan - Landfill Operations | Date: _________ | Berube Notes
Landfill, Alaska
August daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log hours worked.
Notes:
August weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
August monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Complete the backhaul.
Prepare for fall storms and winter weather by securing loose debris, installing winter tires for vehicles and outfitting employees with winter coveralls.
Prepare for subsistence waste and open subsistence waste cell.
Identify and prepare areas for snow dump.
Stockpile cover material.
Complete Freon removal.
Clear grass and brush from burn box area (50 foot radius).
Consolidate, compact and cover working cell.
Notes
Signature Landfill Operator: | Date

## September
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
September daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log the hours worked.
Notes:
September weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
September monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Prepare the heavy equipment for winter.
Inventory and secure left behind hazardous materials that did not make the collection event.
Collect SDS's of hazardous materials. (for training on how to do this give us a call)
Consolidate, compact, cover and close summer cell. (including working face)
Ensure drainage is prepared for winter.
Open winter cell.
Notes
Signature Landfill Operator: | Date

## October
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
October daily check list
If applicable, check and clear electric fence.
Check and clear 50 foot radius for the burn box.
Check the DEC website to ensure there are no burn bans. https://dec.alaska.gov/air/anpms/alaska-fire-restrictions/
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log hours worked.
Notes:
October weekly check list
If applicable, collect elder/customer waste for disposal
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
October monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Update signage if hours have changed.
Clear snow from road as needed.
Inspect and repair fence.
Close any seasonal or bio cells.
Consolidate, compact and cover working cell if possible.
Notes
Signature Landfill Operator: | Date

## November
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
November daily check list
If applicable, check and clear electric fence
Clear snow from the road.
Check and clear 50 foot radius for the burn box.
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log hours worked.
Notes:
November weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
November monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
First aid CPR (every 2 years).
Clear snow from road as needed.
Inspect fire extinguisher and replace if appropriate.
Complete annual respirator fit testing.
Consolidate, compact and cover working cell if possible.
Notes
Signature Landfill Operator: | Date

## December
SWO Annual Plan - Landfill Operations | Date: _________
Landfill, Alaska
December daily check list
If applicable, check and clear electric fence.
Clear snow from road as needed.
Check and clear 50 foot radius for the burn box.
Light and monitor burn box if applicable.
Check and organize the household hazardous waste storage area.
Check and organize salvage area.
Secure equipment and gate.
Log hours worked.
Notes:
December weekly check list
If applicable, collect elder/customer waste for disposal.
If applicable, check in with someone on the city or tribal council with any concerns.
Check stability of berms and insure trenches are no deeper than 4 feet.
Check burn unit for wear or holes.
Check the working face. Is cover and compaction needed?
Check the fence. Is it intact? Is litter blown against it?
Check for windblown litter outside of landfill.
Perform road maintenance depending on season. (Plow road, fill potholes, manage drainage)
Were there any complaints from residents? Make notes.
Notes:
December monthly check list
Complete your monthly landfill visual monitoring form (located on last two pages of the landfill permit)
Clear snow from road as needed.
Cross train with other tribe/city departments.
Consolidate, compact and cover working cell if possible.
Notes
Signature Landfill Operator: | Date